## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | RAILSMART - An Automated Local Ticket Identification and Validation System |  |  |  |  | INSTUTUTE & DEPARTMENT NAME | [6 empty] | A.P SHAH INSTITUTE OF TECHNOLOGY -CSE(DS)
PROJECT GUIDE |  | Prof.Rajashri Chaudhari |  |  |  |  | DATE | [6 empty] | 2025-04-11
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Research paper search | Harsh ,Sakshi,Tanvi | 2024-08-08 | 2024-08-16 | 1 | 100% | bar: WEEK 1 M to WEEK 1 F; WEEK 2 W to WEEK 2 F; WEEK 5 R
1.1.1 | Research paper finalization | Harsh | 2024-08-08 | 2024-08-16 | 1 | 100% | bar: WEEK 1 R to WEEK 2 T; WEEK 2 R to WEEK 2 F; WEEK 5 R
1.2 | Project Title | Harsh, Tanvi | 2024-08-08 | 2024-08-16 | 1 | 100% | bar: WEEK 2 M to WEEK 2 T; WEEK 5 R
1.3 | Abstract | Sakshi | 2024-08-08 | 2024-08-16 | 1 | 100% | bar: WEEK 2 M to WEEK 2 T; WEEK 5 R
1.4 | Objectives | Harsh , Tanvi | 2024-08-08 | 2024-08-16 | 1 | 100% | bar: WEEK 2 M to WEEK 2 T; WEEK 5 R
1.5 | Literature Review | Harsh Mulik | 2024-08-30 | 2024-09-07 | 1 | 100% | bar: WEEK 2 W to WEEK 2 R; WEEK 5 R
1.6 | Problem Definition | Meghraj, Sakshi | 2024-08-30 | 2024-09-21 | 1 | 100% | bar: WEEK 2 W to WEEK 2 R; WEEK 5 R
1.7 | Scope | Tanvi , Sakshi | 2024-08-30 | 2024-09-21 | 3 | 100% | bar: WEEK 2 W to WEEK 2 R; WEEK 5 R
1.8 | Technology stack | Meghraj, Harsh | 2024-08-30 | 2024-09-21 | 3 | 100% | bar: WEEK 2 W to WEEK 2 R; WEEK 5 R
1.9 | Benefits for environment | Tanvi , Harsh | 2024-08-30 | 2024-09-21 | 3 | 100% | bar: WEEK 2 R to WEEK 2 F; WEEK 5 R
1.1 | Benefits for society | Sakshi , Tanvi | 2024-08-30 | 2024-09-21 | 3 | 100% | bar: WEEK 2 R to WEEK 2 F; WEEK 5 R
1.11 | Applications | Tanvi , Harsh | 2024-08-30 | 2024-09-09 | 1 | 100% | bar: WEEK 2 R to WEEK 2 F; WEEK 5 R
2 | Project Design
2.1 | Proposed System | Meghraj ,Tanvi | 2024-08-30 | 2024-09-25 | 4 | 100% | bar: WEEK 2 M to WEEK 3 T; WEEK 5 R
2.2 | Design(Flow Of Modules) | Harsh , Sakshi | 2024-08-30 | 2024-09-25 | 4 | 100% | bar: WEEK 2 M to WEEK 3 W
2.3 | Activity Diagram | Harsh , Tanvi | 2024-08-30 | 2024-09-25 | 4 | 100% | bar: WEEK 3 W to WEEK 3 F; WEEK 5 R
2.4 | Use Case Diagram | Harsh | 2024-08-30 | 2024-09-25 | 4 | 100% | bar: WEEK 3 W to WEEK 3 F; WEEK 5 R
2.5 | Sequence Diagram | Tanvi | 2024-08-30 | 2024-09-25 | 4 | 100% | bar: WEEK 3 W to WEEK 3 F; WEEK 5 R
2.6 | Description Of Use Case | Harsh | 2024-08-30 | 2024-09-25 | 4 | 100% | bar: WEEK 3 W to WEEK 3 F; WEEK 5 R
2.7 | Modules | Meghraj | 2024-08-30 | 2024-09-25 | 4 | 100% | bar: WEEK 4 M to WEEK 4 W; WEEK 5 R
2.7.1 | Application Module | Sakshi, Tanvi | 2024-08-30 | 2024-09-25 | 4 | 100% | bar: WEEK 4 T to WEEK 4 W; WEEK 5 R
2.8 | Preparation Of Report | Harsh | 2024-08-30 | 2024-09-25 | 4 | 100% | bar: WEEK 4 W to WEEK 4 F; WEEK 5 R
3 | Project Implementation
3.1 | Web App Implementation | Meghraj , Harsh | 2024-07-05 | 2025-03-01 | 24 | 100% | bar: WEEK 5 M to WEEK 8 F
3.2 | Module Implementaion | Tanvi , Sakshi | 2024-07-05 | 2025-02-11 | 20 | 100% | bar: WEEK 5 M to WEEK 8 F
3.3 | Model Integration | Tanvi , Harsh | 2024-07-07 | 2025-02-10 | 20 | 100% | bar: WEEK 5 M to WEEK 8 F
3.4 | Interface Implementation | Meghraj , Sakshi | 2024-07-08 | 2025-03-01 | 24 | 100% | bar: WEEK 5 M to WEEK 8 F
4 | Testing
4.1 | Design of Test Cases | Harsh,Tanvi,Sakshi | 2025-03-10 | 2025-04-01 | 4 | 100% | bar: WEEK 2 M; WEEK 5 M to WEEK 5 T; WEEK 5 R
4.2.1 | Ticket Scanning Test | Meghraj,Harsh | 2025-03-11 | 2025-04-01 | 4 | 100% | bar: WEEK 5 T to WEEK 5 R
4.2.2 | Dash Board Testing | Tanvi, Sakshi | 2025-03-12 | 2025-04-01 | 4 | 100% | bar: WEEK 5 W to WEEK 5 R
4.2.3 | Geo-Fence Testing | Meghraj ,Tanvi ,Harsh | 2025-03-13 | 2025-04-01 | 4 | 100% | bar: WEEK 5 R to WEEK 5 F
4.2.4 | Challan Issue Test | Sakshi, Tanvi, Meghraj | 2025-03-14 | 2025-04-01 | 4 | 100% | bar: WEEK 5 R to WEEK 5 F
4.2.5 | Payment Gateway Testing | Harsh , Tanvi | 2025-03-15 | 2025-04-01 | 4 | 100% | bar: WEEK 5 R; WEEK 6 M to WEEK 6 W
4.2.6 | Performance & Load Testing | Meghraj , Sakshi | 2025-03-16 | 2025-04-01 | 4 | 100% | bar: WEEK 5 R; WEEK 6 M to WEEK 6 W
4.2.7 | Llamaparse Accuracy Testing | Harsh , Sakshi | 2025-03-17 | 2025-04-01 | 4 | 100% | bar: WEEK 5 R; WEEK 6 W to WEEK 6 F
4.2.8 | Final Testing & Deployment Readiness | Harsh ,Tanvi ,Sakshi ,Meghraj | 2025-03-18 | 2025-04-01 | 4 | 100% | bar: WEEK 5 R; WEEK 7 M to WEEK 7 T
5 | Report Preparation
5.1 | Black Book | Harsh , Tanvi | 2025-03-21 | 2025-04-11 | 4 | 100% | bar: WEEK 5 R
5.1 | PPT | Harsh , Tanvi | 2025-03-22 | 2025-03-29 | 1 | 100% | bar: WEEK 5 R
5.1 | Gantt Chart | Harsh | 2025-04-10 | 2025-04-11 | 1 | 100% | bar: WEEK 5 R; WEEK 12 M to WEEK 12 F