## Gantchart
GANTT CHART
PROJECT TITLE |  | Drive Safe With AI Assistance |  |  |  |  | INSTUTUTE & DEPARTMENT NAME | [6 empty] | A.P SHAH INSTITUTE OF TECHNOLOGY -CSE(DS)
PROJECT GUIDE |  | Prof. Poonam Pangarkar |  |  |  |  | DATE | [6 empty] | 2025-04-10
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Research paper search | Umesh Nehete , Priyanshu worlikar , Aditi Yadav, Vineet Mhatre | 2024-06-10 | 2024-06-16 | 1 | 100% | bar: WEEK 1 M to WEEK 1 F
1.1.1 | Research paper finalization | Umesh Nehete , Priyanshu worlikar , Aditi Yadav, Vineet Mhatre | 2024-06-17 | 2024-06-24 | 1 | 100% | bar: WEEK 1 R to WEEK 1 F
1.2 | Project Title | Umesh Nehete , Priyanshu worlikar , Aditi Yadav, Vineet Mhatre | 2024-06-25 | 2021-07-01 | 1 | 100% | bar: WEEK 2 M to WEEK 2 T
1.3 | Abstract | Umesh Nehete , Priyanshu worlikar , Aditi Yadav | 2024-07-02 | 2024-07-09 | 1 | 100% | bar: WEEK 2 M to WEEK 2 T
1.4 | Objectives | Aditi Yadav | 2024-07-10 | 2024-07-17 | 1 | 100% | bar: WEEK 2 M to WEEK 2 T
1.5 | Literature Review | Umesh Nehete , Aditi Yadav | 2024-07-18 | 2024-07-25 | 1 | 100% | bar: WEEK 2 W to WEEK 2 R
1.6 | Problem Definition | Priyanshu worlikar , Aditi Yadav | 2024-07-26 | 2024-08-02 | 1 | 100% | bar: WEEK 2 W to WEEK 2 R
1.7 | Scope | Umesh Nehete , Priyanshu worlikar , Aditi Yadav, Vineet Mhatre | 2024-08-03 | 2024-08-10 | 1 | 100% | bar: WEEK 2 W to WEEK 2 R
1.8 | Technology stack | Umesh Nehete , Priyanshu worlikar , Aditi Yadav, Vineet Mhatre | 2024-08-11 | 2024-08-18 | 1 | 100% | bar: WEEK 2 W to WEEK 2 R
1.9 | Applications | Umesh Nehete , Priyanshu worlikar , Aditi Yadav, Vineet Mhatre | 2024-08-19 | 2024-08-26 | 1 | 100% | bar: WEEK 2 R to WEEK 2 F
2 | Project Design
2.1 | Proposed System | Umesh Nehete , Priyanshu worlikar | 2024-08-27 | 2024-09-10 | 2 | 100% | bar: WEEK 3 M to WEEK 3 T
2.2 | Design(Flow Of Modules) | Umesh Nehete , Priyanshu worlikar | 2024-09-11 | 2024-09-18 | 1 | 100% | bar: WEEK 3 M to WEEK 3 W
2.3 | Activity Diagram | Umesh Nehete , Priyanshu worlikar | 2024-09-19 | 2024-09-26 | 1 | 100% | bar: WEEK 3 W to WEEK 3 F
2.4 | Use Case Diagram | Umesh Nehete | 2024-09-27 | 2024-10-04 | 1 | 100% | bar: WEEK 3 W to WEEK 3 F
2.5 | Sequence Diagram | Umesh Nehete , Priyanshu worlikar | 2024-10-05 | 2024-10-12 | 1 | 100% | bar: WEEK 3 W to WEEK 3 F
2.6 | Description Of Use Case | Umesh Nehete Aditi Yadav | 2024-10-13 | 2024-10-20 | 1 | 100% | bar: WEEK 3 W to WEEK 3 F
2.7 | Modules | Umesh Nehete , Priyanshu worlikar , Aditi Yadav, Vineet Mhatre | 2024-10-21 | 2024-10-28 | 1 | 100% | bar: WEEK 4 M to WEEK 4 W
2.7.1 | Application Module | Umesh Nehete , Priyanshu worlikar , Aditi Yadav | 2024-10-29 | 2024-11-05 | 1 | 100% | bar: WEEK 4 T to WEEK 4 W
2.8 | Preparation Of Report | Aditi Yadav | 2024-11-06 | 2024-11-13 | 1 | 100% | bar: WEEK 4 W to WEEK 5 F
3 | Project Implementation
3.1 | Development of GUI | Umesh Nehete , Priyanshu worlikar | 2024-08-14 | 2024-09-28 | 4 | 100% | bar: WEEK 5 M to WEEK 8 F
3.2 | Backend DRF APIs and database setup | Umesh Nehete , Priyanshu worlikar | 2024-09-29 | 2024-10-13 | 2 | 100% | bar: WEEK 5 M to WEEK 8 F
3.3 | Web Socket Implementation | Umesh Nehete , Priyanshu worlikar , | 2024-10-14 | 2024-11-14 | 4 | 100% | bar: WEEK 5 M to WEEK 8 F
3.4 | Integration of Analytics Dashboard | Priyanshu worlikar | 2024-11-15 | 2024-11-29 | 2 | 100% | bar: WEEK 5 M to WEEK 8 F
3.5 | Setting up of Multi Modal Code generation Pipeline | Umesh Nehete , Priyanshu worlikar | 2024-11-30 | 2024-12-30 | 4 | 100% | bar: WEEK 5 M to WEEK 8 F
3.6 | Implementation of Documentation Generation Architecture | Umesh Nehete , Priyanshu worlikar | 2024-12-31 | 2025-01-14 | 2 | 100% | bar: WEEK 5 M to WEEK 8 F
3.7 | Implementation of File System and repsoitories with APIs | vineet mhatre , Aditi yadav | 2025-01-15 | 2025-01-21 | 1 | 100% | bar: WEEK 5 M to WEEK 8 F
3.8 | Implementation of RBAC based authorization in Collaborative | Umesh Nehete , Priyanshu worlikar , Aditi Yadav, Vineet Mhatre | 2025-01-22 | 2025-02-05 | 2 | 100% | bar: WEEK 5 M to WEEK 8 F
3.9 | Integration and deployment of LLM level code generation APIs | Umesh Nehete , Priyanshu worlikar , Aditi Yadav, Vineet Mhatre | 2025-02-06 | 2025-02-20 | 2 | 100% | bar: WEEK 5 M to WEEK 8 F
3.1 | Integration and deployment of Documentation generation APIs | Umesh Nehete , Priyanshu worlikar | 2025-02-21 | 2025-03-07 | 2 | 100% | bar: WEEK 5 M to WEEK 8 F
3.11 | Implementation of Git Commit scheduler | Umesh Nehete , Priyanshu worlikar | 2025-02-21 | 2025-03-07 | 4 | 100% | bar: WEEK 5 M to WEEK 8 F
3.12 | Implementation of Autocommit Generator | Umesh Nehete , Priyanshu worlikar , Aditi Yadav, Vineet Mhatre | 2025-03-08 | 2025-04-08 | 4 | 100% | bar: WEEK 5 M to WEEK 8 F
3.13 | Email Integration for Verification | Priyanshu worlikar | 2025-03-08 | 2025-04-08 | 4 | 100% | bar: WEEK 5 M to WEEK 8 F
3.14 | Implementing Overall theme based system | Umesh Nehete , Priyanshu worlikar , Aditi Yadav, Vineet Mhatre | 2025-03-08 | 2025-04-08 | 4 | 100% | bar: WEEK 5 M to WEEK 8 F
4 | Testing
4.1 | Design of Manual and Automated Test Cases | Umesh Nehete , Priyanshu worlikar , Aditi Yadav, Vineet Mhatre | 2025-03-05 | 2025-03-06 | 1 | 100%
4.2.1 | Unit Testing of Collaborative Editor Edge Cases Module | Umesh Nehete , Priyanshu worlikar , Aditi Yadav, Vineet Mhatre | 2025-03-06 | 2025-03-07 | 1 | 100%
4.2.2 | Unit Testing of Code Generation Pipeline | Umesh Nehete , Priyanshu worlikar , Aditi Yadav, Vineet Mhatre | 2025-03-07 | 2025-03-08 | 1 | 100%
4.2.3 | Unit Testing of Documentation Module | Umesh Nehete , Priyanshu worlikar | 2025-03-08 | 2025-03-09 | 1 | 100%
4.2.4 | Unit Testing of Smart Commits Scheduling Model | Aditi Yadav, Vineet Mhatre | 2025-03-08 | 2025-03-09 | 1 | 100%
4.2.5 | Collaborative Editor Load Test | Umesh Nehete , Priyanshu worlikar | 2025-03-19 | 2025-03-21 | 1 | 100% | bar: WEEK 5 M to WEEK 6 W
4.2.6 | Documentation Scalability | Umesh Nehete , Priyanshu worlikar | 2025-04-02 | 2025-04-03 | 1 | 100% | bar: WEEK 7 M to WEEK 7 T
4.2.7 | Error Handling - Data Corruption | Aditi Yadav, Vineet Mhatre | 2025-04-03 | 2025-04-04 | 1 | 100% | bar: WEEK 7 T to WEEK 7 R
4.2.8 | Error Handling - API Failures | Umesh Nehete , Priyanshu worliker | 2025-04-03 | 2025-04-05 | 1 | 100% | bar: WEEK 7 T to WEEK 7 R
4.2.9 | Regression Testing | Aditi Yadav, Vineet Mhatre | 2025-04-04 | 2025-04-05 | 1 | 100% | bar: WEEK 7 W to WEEK 7 R
4.3.1 | Security - Session Management | Umesh Nehete , Priyanshu worlikar , Aditi Yadav, Vineet Mhatre | 2025-04-04 | 2025-04-06 | 1 | 100% | bar: WEEK 7 W to WEEK 8 F
4.3.2 | ML Model Testing | Umesh Nehete , Priyanshu worlikar , Aditi Yadav, Vineet Mhatre | 2025-04-05 | 2025-04-06 | 1 | 100% | bar: WEEK 7 R to WEEK 8 F
4.3.3 | CLI-Based Input Execution Testing | Umesh Nehete , Priyanshu worlikar , Aditi Yadav, Vineet Mhatre | 2025-04-09 | 2025-04-10 | 1 | 100%
4.3.4 | Dashboard Output Verification Based on Manual Testing | Aditi Yadav, Vineet Mhatre | 2025-04-09 | 2025-04-10 | 1 | 100%
4.3.5 | Integration Testing of All Models and Interfaces Locally | Umesh Nehete , Priyanshu worlikar , Aditi Yadav, Vineet Mhatre | 2025-04-11 | 2025-04-12 | 1 | 100%
4.3.6 | End-to-End Workflow Testing for Different User Scenarios | Aditi Yadav, Vineet Mhatre | 2025-04-11 | 2025-04-12 | 1 | 100%
5 | Report Preparation
5.1 | Black Book | Priyanshu worlikar , Aditi Yadav | 2025-03-21 | 2025-03-28 | 1 | 100%
5.1 | PPT | Priyanshu worlikar , Aditi Yadav | 2025-03-22 | 2025-03-29 | 1 | 100%
5.1 | Gantt Chart | Priyanshu worlikar , Aditi Yadav | 2025-03-28 | 2025-03-28 | 1 | 100% | bar: WEEK 12 M to WEEK 12 F