## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Sentiment-Infused Stock Price Prediction: A Hybrid Model for Capturing Market Sentiments and Financial Trends |  |  |  |  | INSTUTUTE & DEPARTMENT NAME | [6 empty] | A.P SHAH INSTITUTE OF TECHNOLOGY -CSE(DS)
PROJECT GUIDE |  | Prof. Ujjawala Pagare, Prof. Avani Nair |  |  |  |  | DATE | [6 empty] | 2025-04-10
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Research paper search | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2024-06-10 | 2024-06-16 | 1 | 100% | bar: WEEK 1 M to WEEK 1 F
1.1.1 | Research paper finalization | Pravesh Yadav, Mustafa Shaikh | 2024-06-17 | 2024-06-24 | 1 | 100% | bar: WEEK 1 R to WEEK 1 F
1.2 | Project Title | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2024-06-25 | 2021-07-01 | 1 | 100% | bar: WEEK 2 M to WEEK 2 T
1.3 | Abstract | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2024-07-02 | 2024-07-09 | 1 | 100% | bar: WEEK 2 M to WEEK 2 T
1.4 | Objectives | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2024-07-10 | 2024-07-17 | 1 | 100% | bar: WEEK 2 M to WEEK 2 T
1.5 | Literature Review | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2024-07-18 | 2024-07-25 | 1 | 100% | bar: WEEK 2 W to WEEK 2 R
1.6 | Problem Definition | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2024-07-26 | 2024-08-02 | 1 | 100% | bar: WEEK 2 W to WEEK 2 R
1.7 | Scope | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2024-08-03 | 2024-08-10 | 1 | 100% | bar: WEEK 2 W to WEEK 2 R
1.8 | Technology stack | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2024-08-11 | 2024-08-18 | 1 | 100% | bar: WEEK 2 W to WEEK 2 R
1.9 | Applications | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2024-08-19 | 2024-08-26 | 1 | 100% | bar: WEEK 2 R to WEEK 2 F
2 | Project Design
2.1 | Proposed System | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2024-08-27 | 2024-09-10 | 2 | 100% | bar: WEEK 3 M to WEEK 3 T
2.2 | Design(Flow Of Modules) | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2024-09-11 | 2024-09-18 | 1 | 100% | bar: WEEK 3 M to WEEK 3 W
2.3 | Activity Diagram | Mustafa Shaikh, Ankit Purohit | 2024-09-19 | 2024-09-26 | 1 | 100% | bar: WEEK 3 W to WEEK 3 F
2.4 | Use Case Diagram | Mustafa Shaikh, Ankit Purohit | 2024-09-27 | 2024-10-04 | 1 | 100% | bar: WEEK 3 W to WEEK 3 F
2.5 | Sequence Diagram | Mustafa Shaikh, Ankit Purohit | 2024-10-05 | 2024-10-12 | 1 | 100% | bar: WEEK 3 W to WEEK 3 F
2.6 | Description Of Use Case | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2024-10-13 | 2024-10-20 | 1 | 100% | bar: WEEK 3 W to WEEK 3 F
2.7 | Modules | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2024-10-21 | 2024-10-28 | 1 | 100% | bar: WEEK 4 M to WEEK 4 W
2.7.1 | Application Module | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2024-10-29 | 2024-11-05 | 1 | 100% | bar: WEEK 4 T to WEEK 4 W
2.8 | Preparation Of Report | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2024-11-06 | 2024-11-13 | 1 | 100% | bar: WEEK 4 W to WEEK 5 F
3 | Project Implementation
3.1 | Development of Login Page for User Access | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2024-08-14 | 2024-09-28 | 4 | 100% | bar: WEEK 5 M to WEEK 8 F
3.2 | Development of Registration Page | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2024-09-29 | 2024-10-13 | 2 | 100% | bar: WEEK 5 M to WEEK 8 F
3.3 | Design and Setup of Home Page Interface | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2024-10-14 | 2024-11-14 | 4 | 100% | bar: WEEK 5 M to WEEK 8 F
3.4 | User Data and Authentication | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2024-11-15 | 2024-11-29 | 2 | 100% | bar: WEEK 5 M to WEEK 8 F
3.5 | LSTM Model Implementation | Pravesh Yadav, Sumit Shahu | 2024-11-30 | 2024-12-30 | 4 | 100% | bar: WEEK 5 M to WEEK 8 F
3.6 | GRU Model Implementation | Pravesh Yadav, Sumit Shahu | 2024-12-31 | 2025-01-14 | 2 | 100% | bar: WEEK 5 M to WEEK 8 F
3.7 | Ensemble Model Creation | Pravesh Yadav, Sumit Shahu | 2025-01-15 | 2025-01-21 | 1 | 100% | bar: WEEK 5 M to WEEK 8 F
3.8 | Sentiment Analysis using FinBERT | Pravesh Yadav, Sumit Shahu | 2025-01-22 | 2025-02-05 | 2 | 100% | bar: WEEK 5 M to WEEK 8 F
3.9 | Integration Of Machine Learning Models | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2025-02-06 | 2025-02-20 | 2 | 100% | bar: WEEK 5 M to WEEK 8 F
3.1 | Integration of Sentiment Scores with Models | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2025-02-21 | 2025-03-07 | 2 | 100% | bar: WEEK 5 M to WEEK 8 F
3.11 | Integration of ML models to User Interface | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2025-03-08 | 2025-04-08 | 4 | 100% | bar: WEEK 5 M to WEEK 8 F
4 | Testing
4.1 | Design of Test Cases | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2025-07-05 | 2025-07-06 | 1 | 100%
4.2.1 | Login Page Unit testing | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2025-07-06 | 2025-07-07 | 1 | 100%
4.2.2 | Register Page Unit testing | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2025-07-07 | 2025-07-08 | 1 | 100%
4.2.3 | Home Page Unit testing | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2025-07-08 | 2025-07-09 | 1 | 100%
4.2.4 | Integration Testing of above pages | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2025-07-08 | 2025-07-09 | 1 | 100%
4.2.5 | User Reset Password | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2025-07-19 | 2025-07-21 | 1 | 100% | bar: WEEK 5 M to WEEK 6 W
4.2.8 | Accuracy Testing of LSTM Model | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2025-08-02 | 2025-08-03 | 1 | 100% | bar: WEEK 7 M to WEEK 7 T
4.2.9 | Performance Evaluation of GRU Model | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2025-08-03 | 2025-08-04 | 1 | 100% | bar: WEEK 7 T to WEEK 7 R
4.2.10 | Validation of Ensemble Model Output | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2025-08-03 | 2025-08-05 | 1 | 100% | bar: WEEK 7 T to WEEK 7 R
4.3.1 | Testing News Collection Mechanism | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2025-08-04 | 2025-08-05 | 1 | 100% | bar: WEEK 7 W to WEEK 7 R
4.3.2 | Accuracy Assessment of Sentiment Analysis | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2025-08-04 | 2025-08-06 | 1 | 100% | bar: WEEK 7 W to WEEK 8 F
4.3.3 | Verification of Sentiment Score Integration | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2025-08-05 | 2025-08-06 | 1 | 100% | bar: WEEK 7 R to WEEK 8 F
4.3.4 | Integration Testing of ML Models with UI | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2025-08-09 | 2025-08-10 | 1 | 100%
4.3.5 | End-to-End Testing of Prediction Workflow | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2025-08-09 | 2025-08-10 | 1 | 100%
4.3.6 | Error Handling Testing for Data | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2025-08-11 | 2025-08-12 | 1 | 100%
5 | Report Preparation
5.1 | Black Book | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2025-03-21 | 2025-03-28 | 1 | 100%
5.1 | PPT | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2025-03-22 | 2025-03-29 | 1 | 100%
5.1 | Gantt Chart | Pravesh Yadav, Sumit Shahu, Ankit Purohit, Mustafa Shaikh | 2025-03-28 | 2025-03-28 | 1 | 100% | bar: WEEK 12 M to WEEK 12 F